## Summary
M365 Project
Date: | 2018-10-08
CONTENTS
SN | Title | Page No.
1 | Contact Details | 1
2 | Project Plan | 2
3 | Gmail to Office prerequisites | 3
4 | Estimation time for project | 4
No of Sheets in this report : 05

## Contact Details
Escalation Matrix
Name | E-mail ID | Role | Contact No
Aditya Karnati | aditya.karnati@softline.com | Delivery Specialist | 7799634936
Sudipta Mukherjee | sudipta.mukherjee@softline.com | Solution Sales Professional | 9591266644
Chandan Verma | chandan.verma@softline.com | Project Manager | 9967951924
Kiran Babu | Kiran.babu@softline.com | Services Manager | 9819773440

## Project Plan
S.No | Location | Task Name | Owner | User Count | Status | Start Date | End Date | Remarks
1 | N/A | Domain Verification
2 |  | Add & verify published domains to M365 Portal and Azure portal | Local Engineer
3 |  | TXT record in the domain registrar’s website
4 |  | MX. records for Exchange Online, Publish MX records on public facing DNS
5 |  | SRV records for Lync - Ref. sheet SIP Record
6 |  | Publish SIP records on public facing DNS
7 |  | C Name - Ref. sheet CNAME Record
8 |  | Publish CNAME records on public facing DNS
9 |  | AAD Connect (Azure AD Connect)
10 |  | Provision Service Account (Svc-DirSync) | Softline Engineer
11 |  | Installation & configuration of AAD Connect
12 |  | Users syncronization
13 |  | Gmail to O365 Migration
14 |  | Add users in the Portal using .CSV File | Softline Engineer | 300
15 |  | Enable Allow Less secure apps
Enable IMAP In every gamil User
16 |  | Set forwading to all users in gmail
17 |  | Using Imap Migration
24 |  | Sharepoint migration of 2 appalications
25 |  | Migration of 2 sharepoint appalications from one tenant to another tenant | Softline Engineer
Microsoft Intune
26 |  | Microsoft Intune Activation for applying policies | Softline Engineer/local engineer
27 |  | Azure AD Premium Features (AADP) & Self Service Password Reset
28 |  | Custom branding using AADP feature | Softline Engineer
29 |  | Password write back for the domain
30 |  | Enabling Multifactor authentication for users
31 |  | Enabling Self service Password Reset for all the users
32 |  | Showcase Self Service Password Reset
33 |  | Testing (Pre-deployment and Post-Deployment)
34 |  | Mail flow testing (O365 > External) | Softline Engineer
35 |  | Mail flow testing (External > O365)
36 |  | Transport Rules
37 |  | DLP policies
38 |  | Advanced Threat Protection
39 |  | Test all Office365 E3 product features
40 |  | Deployment of Intune
41 |  | EMS Workshop | Softline Engineer
42 |  | Mobile Application Management – Showcase Managed Office Mobile Apps (Word, Excel, PowerPoint, OneNote & OneDrive for Business) on iOS & Android Device.
43 |  | Showcase Remote Wipe – Full Wipe & Selective Wipe.
44 |  | Configure Device Enrollment for iOS, Windows & Android Devices.
45 |  | Configure Device Compliance Policies.Configure Device Management Policies (PIN, Password Policy, Encryption, Disable Screen Capture, and Disable Camera on Mobile Devices etc.)
46 |  | Configure Device Compliance Policies
47 |  | Facilitate Deployment of Apps on Mobile Devices. Deploy Outlook for iOS & Android that has been recently released using intune.
48 |  | Provision Conditional Access to Exchange Online on iOS, Android & Windows Mobile Device.
49 |  | Provision Conditional Access to One Drive for Business on iOS, Android & Windows Mobile Device.
50
51 | Migration Activites (Migration Activites END User)
52 | Hyderabad | Installation of O365 office | Local Administrator/Softline Engineer | 200
53 |  | Installation of Skype & pass the username/password
54 |  | Installation of MS Teams & pass the username/password
55 |  | Windows 10 upgrade
56 |  | All O365 product configuration like Skype, MS Teams, EMS etc.
57 |  | Outlook Configuration
58 |  | Office Apps, MS Outlook Configuration on mobile
59 |  | Documentation with training material preperation and send communication org wide
60 |  | Daily progress update to all Stakeholders
61 |  | User training for O365 products like MS Teams, Skype for business, Outlook, Planner, Language translator.- Weekly Friday
62 | Migration Activites (Migration Activites END User)
63 | US | Installation of O365 office | Local Administrator/Softline Engineer | 50
64 |  | Installation of Skype & pass the username/password
65 |  | Installation of MS Teams & pass the username/password
66 |  | Windows 10 upgrade
67 |  | All O365 product configuration like Skype, MS Teams, EMS etc.
68 |  | Outlook Configuration
69 |  | Office Apps, MS Outlook Configuration on mobile
70 |  | Documentation with training material preperation and send communication org wide
71 |  | Daily progress update to all Stakeholders
72 |  | User training for O365 products like MS Teams, Skype for business, Outlook, Planner, Language translator.- Weekly Friday
73 | Migration Activites (Migration Activites END User)
74 | Malaysia | Installation of O365 office | Local Administrator/Softline Engineer | 50
75 |  | Installation of Skype & pass the username/password
76 |  | Installation of MS Teams & pass the username/password
77 |  | Windows 10 upgrade
78 |  | All O365 product configuration like Skype, MS Teams, EMS etc.
79 |  | Outlook Configuration
80 |  | Office Apps, MS Outlook Configuration on mobile
81 |  | Documentation with training material preperation and send communication org wide
82 |  | Daily progress update to all Stakeholders
83 |  | User training for O365 products like MS Teams, Skype for business, Outlook, Planner, Language translator.- Weekly Friday

## Gmail to Office prerequisites
Enable IMAP Steps: Step1: Login Gmail user mail id. Step2: In the top right, click Settings . Step3: Click the Forwarding and POP/IMAP tab. Step4: In the "IMAP Access" section, select Enable IMAP.
3. Allow Less secure apps Step1:Go to the Less secure apps section of your Google Account. Step2:Turn on Allow less secure apps. If you don't see this setting, your administrator might have turned off less secure app account access.
1. Enable IMAP. 2. Set Forwarding With onmicrosoft.com 3. Allow Less secure apps
Set Forwarding with onmicrosoft.com mail id: Step1: login to Gmail account web mail. Step2: In the top right, click Settings . Step3: Click Settings. Step4: Click the Forwarding and POP/IMAP tab. Step5: In the "Forwarding" section, click Add a forwarding address. Step6: Enter the email address with .onmicrosoft.com you want to forward messages to. Step7: Click Next Proceed OK. Step8: At the bottom of the page, click Save Changes.
Enabling less secure apps to access accounts: Note: This is for administrator with global Admin Credentials “Allow secure apps”. After that follow the below steps Step1: login to user Gmail Global Admin id. Step2: Click Security > Basic settings. Step3: Under Less secure apps, select go to settings for less secure apps. Step4: In the sub window, select the Allow users to manage their access to less secure apps radio button Once you've set Allow users to manage their access to less secure apps to on, affected users within the selected group or Organizational Unit will be able to toggle access for less secure apps on or off themselves. Enforcing access to less secure apps for all users: Step1: Sign in with global admin credentials. Step2: Click Security > Basic settings. Step3: Under Less secure apps, select Go to settings for less secure apps. Step4: In the sub window, select the Enforce access to less secure apps for all users radio button.

## Estimation time for project
Task to Do | Duration
AAD Connect (Azure AD Connect) | 3-Days
Gmail to O365 Migration | 6-weeks
Sharepoint migration of 2 appalications | *Time to be discussed
Setup EMS Portal | 1 week
Integration of EMS + O365 | 1 week
EMS Policy roll out | 3 weeks
UAT | One (1) Week
EMS Roll out all users | 1 month