## Project Plan
S.No | Location | Task Name | Owner | User Count | Status | Start Date | End Date | Remarks
1 | N/A | Domain Verification
2 |  | Add & verify published domains to M365 Portal and Azure portal | Local Engineer
3 |  | TXT record in the domain registrar’s website
4 |  | MX. records for Exchange Online, Publish MX records on public facing DNS
5 |  | SRV records for Lync - Ref. sheet SIP Record
6 |  | Publish SIP records on public facing DNS
7 |  | C Name - Ref. sheet CNAME Record
8 |  | Publish CNAME records on public facing DNS
9 |  | AAD Connect (Azure AD Connect)
10 |  | Provision Service Account (Svc-DirSync) | Softline Engineer
11 |  | Installation & configuration of AAD Connect
12 |  | Users syncronization
13 |  | Gmail to O365 Migration
14 |  | Add users in the Portal using .CSV File | Softline Engineer | 200
15 |  | Enable Allow Less secure apps
16 |  | Set forwading to all users in gmail
17 |  | Using Systool do migration of mails, contacts, calenders
18 |  | Enable Allow Less secure apps |  | 50
19 |  | Set forwading to all users in gmail
20 |  | Using Systool do migration of mails, contacts, calenders
21 |  | Enable Allow Less secure apps |  | 50
22 |  | Set forwading to all users in gmail
23 |  | Using Systool do migration of mails, contacts, calenders
24 |  | Sharepoint migration of 2 appalications
25 |  | Migration of 2 sharepoint appalications from one tenant to another tenant | Softline Engineer
26
27 |  | Azure AD Premium Features (AADP) & Self Service Password Reset
28 |  | Custom branding using AADP feature | Softline Engineer
29 |  | Password write back for the domain
30 |  | Enabling Multifactor authentication for users
31 |  | Enabling Self service Password Reset for all the users
32 |  | Showcase Self Service Password Reset
33 |  | Testing (Pre-deployment and Post-Deployment)
34 |  | Mail flow testing (O365 > External) | Softline Engineer
35 |  | Mail flow testing (External > O365)
36 |  | Transport Rules
37 |  | DLP policies
38 |  | Advanced Threat Protection
39 |  | Test all Office365 E3 product features
40 |  | Deployment of Intune
41 |  | EMS Workshop | Softline Engineer
42 |  | Mobile Application Management – Showcase Managed Office Mobile Apps (Word, Excel, PowerPoint, OneNote & OneDrive for Business) on iOS & Android Device.
43 |  | Showcase Remote Wipe – Full Wipe & Selective Wipe.
44 |  | Configure Device Enrollment for iOS, Windows & Android Devices.
45 |  | Configure Device Compliance Policies.Configure Device Management Policies (PIN, Password Policy, Encryption, Disable Screen Capture, and Disable Camera on Mobile Devices etc.)
46 |  | Configure Device Compliance Policies
47 |  | Facilitate Deployment of Apps on Mobile Devices. Deploy Outlook for iOS & Android that has been recently released using intune.
48 |  | Provision Conditional Access to Exchange Online on iOS, Android & Windows Mobile Device.
49 |  | Provision Conditional Access to One Drive for Business on iOS, Android & Windows Mobile Device.
50
51 | Migration Activites (Migration Activites END User)
52 | Hyderabad | Installation of O365 office | Local Administrator/Softline Engineer | 200
53 |  | Installation of Skype & pass the username/password
54 |  | Installation of MS Teams & pass the username/password
55 |  | Windows 10 upgrade
56 |  | All O365 product configuration like Skype, MS Teams, EMS etc.
57 |  | Outlook Configuration
58 |  | Office Apps, MS Outlook Configuration on mobile
59 |  | Documentation with training material preperation and send communication org wide
60 |  | Daily progress update to all Stakeholders
61 |  | User training for O365 products like MS Teams, Skype for business, Outlook, Planner, Language translator.- Weekly Friday
62 | Migration Activites (Migration Activites END User)
63 | US | Installation of O365 office | Local Administrator/Softline Engineer | 50
64 |  | Installation of Skype & pass the username/password
65 |  | Installation of MS Teams & pass the username/password
66 |  | Windows 10 upgrade
67 |  | All O365 product configuration like Skype, MS Teams, EMS etc.
68 |  | Outlook Configuration
69 |  | Office Apps, MS Outlook Configuration on mobile
70 |  | Documentation with training material preperation and send communication org wide
71 |  | Daily progress update to all Stakeholders
72 |  | User training for O365 products like MS Teams, Skype for business, Outlook, Planner, Language translator.- Weekly Friday
73 | Migration Activites (Migration Activites END User)
74 | Malaysia | Installation of O365 office | Local Administrator/Softline Engineer | 50
75 |  | Installation of Skype & pass the username/password
76 |  | Installation of MS Teams & pass the username/password
77 |  | Windows 10 upgrade
78 |  | All O365 product configuration like Skype, MS Teams, EMS etc.
79 |  | Outlook Configuration
80 |  | Office Apps, MS Outlook Configuration on mobile
81 |  | Documentation with training material preperation and send communication org wide
82 |  | Daily progress update to all Stakeholders
83 |  | User training for O365 products like MS Teams, Skype for business, Outlook, Planner, Language translator.- Weekly Friday

## Total Migrate User and Status
S.No | Display Name | City | Current OS | O365 Installtion (Yes/No) | Teams (Yes/No) | Skype for Business | Windows 10 pro (Yes/No) | Sign Off | Migration Full Status

## Owners Checklist
Checklist Activity | Owner